## Requirement_Traceability_Matrix
REQUIREMENTS TRACEABILITY MATRIX
Project Name | Worth the Words
Project Type | System Requirements
Project Start Date | 2025-01-13
Project End Date | 2025-04-22
Project Sponsor | James Chrisman
Project Manager/Department | Geek Squad
ID | Technical Assumption(s) and/or Customer Need(s) | Functional Requirement | Status | Technical Specification | System Component(s) | Date Baselined | Date Designed | Date Tested | Date Implemented | Additional Comments
001 | Calendar placement at bottom of all pages. | The calendar is found on the bottom of all pages of the website. | In Progress | Calendar and Event Spec | Frontend UI |  |  |  |  | Discontinued: Calendar is on the Events page. Design issues if placed in the footer.
002 | Calendar updates with website. | The calendar shall update as the website is updated. | In Progress | Calendar and Event Spec | Backend UI | 2/20/2025 | 2/22/2025 | 2/24/2025
003 | Calendar is interactive for visitors. | The calendar shall be interactive so visitors can click events | In Progress | Calendar and Event Spec | Frontend UI | 2/20/2025 | 2/22/2025 | 2/24/2025
004 | Interactive calendar shows event information when an event is selected. | Clicking an event in the Calendar shall lead to information on the event. | In Progress | Calendar and Event Spec | Frontend UI | 2/20/2025 | 2/22/2025 | 2/24/2025
005 | Volunteer sign ups can be accessed from calendar. | The Calendar shall be a way for volunteers to sign up. | In Progress | Calendar and Event Spec | Frontend UI | 2/20/2025 | 2/22/2025 | 2/24/2025
006 | Administrator access required for updating calendar. | The administrator shall need access to update the calendar. | In Progress | Calendar and Event Spec | Backend UI | 2/20/2025 | 2/22/2025 | 2/24/2025
007 | upcoming events displayed on calendar. | The event calendar shall display upcoming events. | In Progress | Calendar and Event Spec | Frontend UI | 2/20/2025 | 2/22/2025 | 2/24/2025
008 | volunteer opportunities shown on calendar. | The event calendar shall display volunteer opportunities. | In Progress | Calendar and Event Spec | Frontend UI | 2/20/2025 | 2/22/2025 | 2/24/2025
009 | RSVP option available on event calendar. | The event calendar shall allow users to RSVP. | In Progress | Calendar and Event Spec | Frontend UI | 2/20/2025 | 2/22/2025 | 2/24/2025
010 | Event reminders sent to users. | The event calendar shall send users event reminders. | In Progress | Calendar and Event Spec | Frontend UI | 2/20/2025 | 2/22/2025 | 2/24/2025
011 | administrators can create new events on calendar. | The Event Calendar Module will allow administrators to create new event entries. | In Progress | Calendar and Event Spec | Backend UI | 2/20/2025 | 2/22/2025 | 2/24/2025
012 | administrators can modify events on calendar. | The Event Calendar Module will allow administrators to modify existing event details. | In Progress | Calendar and Event Spec | Backend UI | 2/20/2025 | 2/22/2025 | 2/24/2025
013 | Users can search for events by date or category. | The Event Calendar Module will allow users to search for events by date or category. | In Progress | Calendar and Event Spec | Frontend UI | 2/20/2025 | 2/22/2025 | 2/24/2025
014 | easily accessible donation button on all pages. | Donation button shall be accessible on all pages on the top bar. | In Progress | Donation Spec | Frontend UI | 2/13/2025 | 2/16/2025 | 2/23/2025
015 | donation button reroutes user to PayPal. | The Donation Button shall reroute the visitor to PayPal. | In Progress | Donation Spec | Donation Integration | 3/6/2025 | 3/29/3025 | 3/30/3025 |  | Possible integration into website
016 | Offers donors to give their information | The Donation Button shall offer donors to give their information. | In Progress | Donation Spec | Donation Integration | 3/6/2025 | 3/29/3025 | 3/30/3025
017 | Recurring donations offered. | The donation integration shall allow recurring donations. | In Progress | Donation Spec | Donation Integration | 3/6/2025 | 3/29/3025 | 3/30/3025
018 | One-time donations offered. | The Donation Button shall allow for one-time charges for donations. | In Progress | Donation Spec | Donation Integration | 3/6/2025 | 3/29/3025 | 3/30/3025
019 | administrator access required to change donation types. | The Administrator shall need access to edit donation types. | In Progress | Donation Spec | Donation Integration | 3/6/2025 | 3/29/3025 | 3/30/3025
020 | ease-of-use donation platform needed. | The donation integration shall provide an ease-of-use donation platform. | In Progress | Donation Spec | Donation Integration | 3/6/2025 | 3/29/3025 | 3/30/3025
021 | donation platform must be secure. | The donation integration shall provide a secure donation platform. | In Progress | Donation Spec | Donation Integration | 3/6/2025 | 3/29/3025 | 3/30/3025
022 | administrators can manage donation subscriptions. | The Donation Module will allow administrators to manage donation subscriptions. | In Progress | Donation Spec | Donation Integration | 3/6/2025 | 3/29/3025 | 3/30/3025
023 | payment conformations sent to donors. | The Donation Module will allow notifications for payment confirmations to be sent. | In Progress | Donation Spec | Donation Integration | 3/6/2025 | 3/29/3025 | 3/30/3025
024 | Donation history for donors. | The Donation Module will allow donors to manage their donation history. | In Progress | Donation Spec | Donation Integration | 3/6/2025 | 3/29/3025 | 3/30/3025
025 | Donors can choose to receive newsletters. | The Donation Banner will have a check box for getting a newsletter | In Progress | Donation Spec | Donation Integration |  |  |  |  | Discontinued: The Newsletter sign-up is only in the footer
026 | automatically saved volunteer forms. | The Volunteer Form will allow for user information to be automatically saved. | In Progress | Volunteer Spec | Frontend UI | 2/20/2025 | 2/22/2025 | 2/24/2025
027 | different volunteer positions available for sign up. | The Volunteer Sign Up shall show volunteers positions that they can put in for. | In Progress | Volunteer Spec | Frontend UI | 3/21/2025 | 3/22/2025 | 3/27/2025
028 | volunteer page shows information on opportunities for volunteers. | The Volunteer Page shall display information on volunteer opportunities. | In Progress | Volunteer Spec | Frontend UI | 3/21/2025 | 3/22/2025 | 3/27/2025
029 | all available events shown on volunteer page. | The Volunteer Sign Up shall display all available events for volunteers. | In Progress | Volunteer Spec | Frontend UI | 2/20/2025 | 2/22/2025 | 2/24/2025
030 | Sign-up page facilitates the registering process for volunteers. | The Volunteer sign-up shall facilitate the process for users to register | In Progress | Volunteer Spec | Backend UI | 2/20/2025 | 2/22/2025 | 2/24/2025
031 | registrations for volunteer sign-ups are confirmed automatically. | The volunteer sign-up shall automatically confirm registrations. | In Progress | Volunteer Spec | Backend UI | 2/20/2025 | 2/22/2025 | 2/24/2025
032 | credentials for specific jobs can be submitted on volunteer sign-ups. | The Volunteer Form will allow users to submit their credentials for specific jobs | In Progress | Volunteer Spec | Frontend UI | 3/21/2025 | 3/22/2025 | 3/27/2025
033 | simple outlet for questions provided on contact form. | The contact form shall provide a simple outlet for questions. | In Progress | Contact Spec | Frontend UI | 2/20/2025 | 2/22/2025 | 2/23/2025 |  | FAQ webpage
034 | Increased community engagement. | The contact form shall increase community engagement. | In Progress | Contact Spec | Frontend UI | 2/20/2025 | 2/22/2025 | 2/23/2025
035 | Sponsor and partner availability on contact form. | The contact form shall provide opportunities for sponsors or partners to reach out | In Progress | Contact Spec | Frontend UI | 2/20/2025 | 2/22/2025 | 2/23/2025
036 | Email or wix dashboard allows contact form submissions to be viewed. | The contact form shall have the option for submission to be viewed via email or Wix dashboard | In Progress | Contact Spec | Backend UI | 2/20/2025 | 2/22/2025 | 2/23/2025
037 | Questions can be submitted through contact form. | The Contact Form will allow users to submit questions | In Progress | Contact Spec | Frontend UI | 2/20/2025 | 2/22/2025 | 2/23/2025
038 | specific information can be aquired by users on contact form. | The Contact Form will allow users to get specific information | In Progress | Contact Spec | Frontend UI | 2/20/2025 | 2/22/2025 | 2/23/2025
039 | Email availability for users to receive newsletters and event updates. | The Contact Form will allow you to put in your email to be emailed about events and a newsletter. | In Progress | Contact Spec | Frontend UI | 2/20/2025 | 2/22/2025 | 2/23/2025
040 | Our Story Page has depth of the companies background. | The Our Story Page shall go into more depth to the background of the company | In Progress | Our Story Page Spec | Frontend UI | 3/20/2025 | 3/17/2025 | 3/30/3025
041 | Newsletter sign-up allows users to sign up for email updates. | The newsletter sign-up shall provide users with the ability to subscribe to email updates. | In Progress | Newsletter Spec | Frontend UI | 2/20/2025 | 2/22/2025 | 2/23/2025
042 | Newsletter ensures supporters are informed about latest news. | The newsletter sign-up shall ensure supporters are informed about the latest news. | In Progress | Newsletter Spec | Frontend UI | 2/20/2025 | 2/22/2025 | 2/23/2025
043 | New volunteer opportunities are shown on newsletter. | The newsletter sign-up shall ensure supporters are informed about the latest opportunities. | In Progress | Newsletter Spec | Frontend UI | 2/20/2025 | 2/22/2025 | 2/23/2025
044 | Current projects shown on project showcase. | The project showcase shall highlight current projects. | In Progress | Project Showcase Spec | Frontend UI | 2/13/2025 | 2/16/2025 | 2/23/2025
045 | Completed projects shown on project showcase. | The project showcase shall highlight completed projects. | In Progress | Project Showcase Spec | Frontend UI | 2/13/2025 | 2/16/2025 | 2/23/2025
046 | project showcase needs to increase transperency. | The project showcase shall increase transparency. | In Progress | Project Showcase Spec | Frontend UI | 2/13/2025 | 2/16/2025 | 2/23/2025
047 | project showcase needs to increase community engagement. | The project showcase shall increase community engagement. | In Progress | Project Showcase Spec | Frontend UI | 2/13/2025 | 2/16/2025 | 2/23/2025
048 | song catalog should have a list of songs made by participants. | The song catalog shall list a number of songs made by youth participants. | In Progress | Song Catalog Spec | Frontend UI | 2/13/2025 | 2/16/2025 | 2/23/2025
049 | pause and play functionality on song catalog. | The song catalog shall have pause/play functionality. | In Progress | Song Catalog Spec | Frontend UI | 2/13/2025 | 2/16/2025 | 2/23/2025
050 | volume slider functionality on song catalog. | The song catalog shall have a volume slider. | In Progress | Song Catalog Spec | Frontend UI |  |  |  |  | Discontinued: There is no element for this for our music player and we tried alternative music players, but none to our interest.
051 | A way to share songs from the song catalog. | The song catalog shall have a share button for each song. | In Progress | Song Catalog Spec | Frontend UI | 2/13/2025
052 | Administrators want to get certain feedback. | The Questionnaire Module shall allow administrators to customize questions to get information or input they desire. | In Progress | Questionnaire Spec | Frontend UI | 4/3/2025
053 | Design modifications for the Questionnaire. | The Questionnaire Module shall allow administrators to modify the design of the form to fit the format they desire. | In Progress | Questionnaire Spec | Frontend UI | 4/3/2025
054 | Multiple answer options to be available for each question. | The Questionnaire Module shall allow administrators to configure questions to be short answers, paragraphs, multiple choice, checkboxes, and dropdown question types. | In Progress | Questionnaire Spec | Frontend UI | 4/3/2025
055 | Questions can be added, removed, or reordered. | The Questionnaire Module shall allow administrators to add, remove, or reorder questions as needed | In Progress | Questionnaire Spec | Frontend UI | 4/3/2025
056 | Prioritized questions that are important for feedback. | The Questionnaire Module shall allow mandatory questions that users must answer before submitting the form. | In Progress | Questionnaire Spec | Frontend UI | 4/3/2025
057 | Questionnaire form that allows saving. | The Questionnaire Module shall allow users to save the form and return to complete it later by having an autosave feature. | In Progress | Questionnaire Spec | Frontend UI | 4/3/2025
058 | Previewing of a Questionnaire form. | The Questionnaire Module shall allow administrators to preview the form before publishing it. | In Progress | Questionnaire Spec | Frontend UI | 4/3/2025
059 | Reviewing submitted forms from users. | The Questionnaire Module shall allow administrators to view the answers the users submitted | In Progress | Questionnaire Spec | Backend UI | 4/3/2025
060 | A way to protect user's information on submitted forms. | The Questionnaire Module shall allow data security and privacy by encrypting user responses. | In Progress | Questionnaire Spec | Backend UI | 4/3/2025
061 | Process to check responses are in correct formatting. | The Questionnaire Module shall allow real-time data validation of user input to ensure the data is in the correct format (email addresses and phone numbers). | In Progress | Questionnaire Spec | Frontend UI | 4/3/2025
062 | Connect social media apps using clickable links. | Social media integration shall integrate social media links. | In Progress | Social Media Spec | Social Media Integration | 2/13/2025 | 2/16/2025 | 2/23/2025
063 | Connecting social media content into the website. | Social media integration shall integrate social media feeds. | In Progress | Social Media Spec | Social Media Integration | 2/13/2025 | 2/16/2025 | 2/23/2025
064 | Increasing of user engagement. | Social media integration shall improve engagement. | In Progress | Social Media Spec | Social Media Integration | 2/13/2025 | 2/16/2025 | 2/23/2025
065 | Use of social media to become more known. | Social media integration shall improve visibility. | In Progress | Social Media Spec | Social Media Integration | 2/13/2025 | 2/16/2025 | 2/23/2025
066 | HTTPS to keep the website secure. | The site shall have usage of Https so that the website will be secure. | In Progress | Security Spec | Backend UI | 2/13/2025 | 2/16/2025 | 2/23/2025
067 | A plug-in will be used to protect any personal information given. | The website shall have a security plug-in to secure personal information. | In Progress | Security Spec | Backend UI
068 | Sensitive information is encrypted to protect users. | Personal information shall be encrypted and not stored in plain text. | In Progress | Security Spec | Backend UI
069 | Buttons to redirect to different pages of the website. | The header shall need buttons to redirect you to each of the different areas of the site. | In Progress | Header Spec | Frontend UI | 2/13/2025 | 2/16/2025 | 2/23/2025
070 | Instagram and Facebook can be accessed through a clickable banner. | The header shall have a link for Instagram and Facebook. | In Progress | Header Spec | Social Media Integration | 2/13/2025 | 2/16/2025 | 2/23/2025
071 | The home page can be accessed through a clickable title. | The header shall have a clickable title to take you back to the home page. | In Progress | Header Spec | Frontend UI | 2/13/2025 | 2/16/2025 | 2/23/2025
072 | A plug-in will be used to track and collect data of user interaction. | The addition of analytics through a plug-in shall allow for data analysis of the site. | In Progress | Analytics spec | Frontend UI
073 | Enabling sales tracking to monitor sales. | Sales analytics in square shall allow for sales analytics. | In Progress | Analytics spec | Backend UI
074 | Analytics are accessed only be Administrators. | The analytics shall allow only administrators access. | In Progress | Analytics spec | Backend UI | 3/6/2025 | 3/29/2025 | 3/30/3025
075 | Analytics can be viewed and compared in different formats. | The administrators shall have different formats to view analytics, and how to compare the data. | In Progress | Analytics spec | Backend UI | 3/6/2025 | 3/29/2025 | 3/30/3025
076 | Responses are sent to Google Sheets automatically for viewing. | The Questionnaire form shall auto export to google sheet to allow for manipulation, and data viewing. | In Progress | Analytics spec | Backend UI |  |  |  |  | Discontinued: We will be using a Wix Form, so submissions will go into Wix.
077 | A counter tracking the number of people that helped. | The analytics shall have a counter that can be set by the owner for how many people have been helped. | In Progress | Analytics spec | Frontend UI | 3/20/2025 | 3/24/2025 | 3/30/3025
078 | Staff can manage blogs. | The content management system shall empower staff to easily update blogs | In Progress | CMS Spec | Frontend UI |  |  |  |  | Discontinued: There is no longer going to be a blog page (out-of-scope)
079 | Staff can update events. | The content management system shall empower staff to easily update events. | In Progress | CMS Spec | Frontend UI | 2/20/2025 | 2/22/2025 | 2/23/2025
080 | Staff can manage project reports. | The content management system shall empower staff to easily update project reports. | In Progress | CMS Spec | Frontend UI | 2/20/2025 | 2/22/2025 | 2/23/2025
081 | No technical expertise is required to use CMS. | The content management system shall require no technical expertise. | In Progress | CMS Spec | Frontend UI | 2/20/2025 | 2/22/2025 | 2/23/2025
082 | A widget stays visible when scrolling | The Widget shall scroll with the page. | In Progress | Widget Spec | Frontend UI |  |  |  |  | Discontinued: Widgets will stay still and only be present on the About page
083 | A widget will rotate sponsors as the user stays on the page. | The Widget shall rotate sponsors while visitors are on the page. | In Progress | Widget Spec | Frontend UI | 2/13/2025 | 2/18/2025 | 2/23/2025
084 | A widget displaying the number of people that helped. | The Widget shall display the number of people helped. | In Progress | Widget Spec | Frontend UI | 3/20/2025 | 3/24/2025 | 3/30/3025
085 | A widget displaying the number of donators. | The Widget shall display the number of donators. | In Progress | Widget Spec | Frontend UI | 3/20/2025 | 3/24/2025 | 3/30/3025
086 | A widget found on all pages. | The Widget shall be found on all pages. | In Progress | Widget Spec | Frontend UI |  |  |  |  | Discontinued: Widgets will only be present on the About page
087 | A widget allowing access to the organization's social media. | The Widget shall also act as easy access to social media of the organization. | In Progress | Widget Spec | Frontend UI | 2/13/2025 | 2/18/2025
088 | Mobile optimization adapts and adjusts the content on mobile devices. | The mobile optimization shall have a responsive design for mobile users. | In Progress | Mobile Optimization Spec | Frontend UI | 2/13/2025 | 2/22/2025
089 | The website is easy to use and functional on mobile devices. | The mobile optimization shall maintain useability without sacrificing functionality. | In Progress | Mobile Optimization Spec | Frontend UI | 2/13/2025 | 2/22/2025
090 | Content of the website will be improved for new users. | The website shall be reorganized for visitors. | In Progress | Non-Functional Spec | Frontend UI | 4/3/2025 |  |  |  | Tutorial of the Webpage functions
091 | A section on experiences/feedback of youth participants and parents. | The review section shall show testimonies from youth participants and parents regarding their experiences with Worth the Words. | In Progress | Reviews Spec | Frontend UI | 4/3/2025
092 | Number of volunteer hours of volunteers displayed on widgets. | The volunteer hours widget shall display the number of volunteer hours worked by Worth the Words volunteers. | In Progress | Volunteer Hours Widget Spec | Frontend UI | 3/20/2025 | 3/24/2025 | 3/30/3025
093 | Users can access content depending on screen sizes. | The guidelines for the page shall let a variety of users access it depending on their screen size. | In Progress | Non-Functional Spec | Frontend UI | 4/3/2025
094 | Consistent design of the header and footer across all pages. | The guidelines for the page shall have the header and footer will be the same across pages. | In Progress | Non-Functional Spec | Frontend UI | 2/13/2025 | 2/22/2025 | 2/23/2025
095 | Outlines to interpret gathered data. | A guide for how to use the analytics and what the data may mean. | In Progress | Non-Functional Spec | Backend UI | 4/3/2025
096 | Outlines to text and image modifications. | A guide for how to modify text and images. | In Progress | Non-Functional Spec | Backend UI | 4/3/2025
097 | Outlines for troubleshooting. | A guide for troubleshooting. | In Progress | Non-Functional Spec | Backend UI | 4/3/2025
Note on A8: • ID: A unique ID number used to identify the requirement in the requirement traceability log.
Note on B8: • Technical Assumptions or Customer Needs: This column should be populated with a description of the technical assumption or customer need linked to the functional requirement.
Note on C8: • Functional Requirement: This column should be populated with a description of the functional requirement.
Note on D8: • Status: This column should be populated with the current status of the functional requirement.
Note on E8: • Technical Specification: This column should be populated with a description of the technical specification linked to the functional requirement.
Note on F8: • System Component(s): This column should be populated with a description of the system component(s) linked to the functional requirement.